## Bug Report
Project Name |  |  | Environment
Tester's Name |  | Abdullah Al Nouman | Reviewed By
Date Tested |  | 2024-11-20 | Version
Issue Id | Module | Issue Title | Description | Steps to Reproduce | Issue Type | Priority | Severity | Actual Result | Expected Result | Attachment
1 | Statement | Export Button to Generate Statement Excel Sheet Not Working | The Export button in the Statement module is not functioning for the System user. When clicked, it fails to generate and download the Excel sheet. This issue affects the ability to export statements for analysis. |  | Bug | High | High |  | Clicking the Export button should generate and download the statement in Excel format. | https://drive.google.com/file/d/18Ffg3AWwoSbvFDr8A1UE2blSX7poc1fp/view?usp=drive_link
2 | Payment | Input Field Size Mismatch and Placeholder Text Truncation | In the Payment module for the System user, the size of the two input fields is inconsistent. Additionally, the placeholder text in the first input field is truncated due to insufficient space, making it unreadable. |  | Bug | Medium | Minor |  | - Both input fields should have the same size. - The placeholder text in the first input field should be fully visible without truncation. | https://drive.google.com/file/d/18qNR9DppoGVGMHh53_Hmtz6EMOh9kZDD/view?usp=drive_link
3 | Create User | Duplicate User Creation with Same NID Allowed | In the Create User module for the Admin user, multiple users can be created using the same NID number. The NID should be unique for each user to prevent duplication and ensure data integrity. |  | Bug | High | Major |  | The system should validate the NID field and prevent the creation of users with duplicate NID numbers. A clear error message should be displayed, such as "NID already exists". | https://drive.google.com/file/d/1Oe_IB6OksMykWl2f6c-NJAdF9VNZuCwy/view?usp=drive_link
4 | Create User | Input Fields Not Cleared After Creating a New User | In the Create New User module for the Admin user, the input fields remain filled with the previously entered data after successfully creating a new user. This can lead to accidental duplication or incorrect data entry. |  | Bug | Medium | Minor |  | The input fields should be cleared automatically after successfully creating a new user, ready for a new entry. | https://drive.google.com/file/d/1pmuy3WSQPBlbGeeeIDsJlv8sIxGWBB5O/view?usp=drive_link
5 | Create User | Special Characters Allowed in Account Creation | In the Create User module for the Admin user, accounts can be created using special characters in the account number field, which is incorrect. The field should only allow numeric values to ensure data integrity and compliance with validation rules. |  | Bug | High | Major |  | The account number field should only accept numeric inputs and reject any input containing special characters or alphabets. | https://drive.google.com/file/d/1zXB0Bn2a-0eUx7yio2MV4bs-AXdVRmAc/view?usp=drive_link
6 | Statement | Export Button to Generate Statement Excel Sheet Not Working | The Export button in the Statement module is not functioning for the Agent user. When clicked, it fails to generate and download the Excel sheet. This issue affects the ability to export statements for analysis. |  | Bug | High | High |  | Clicking the Export button should generate and download the statement in Excel format. | https://drive.google.com/file/d/1CXKu0IIQda-ZsMtmbSrkMjw5rm4Ykv7i/view?usp=drive_link
7 | Payment | Input Field Size Mismatch and Placeholder Text Truncation | In the Payment module for the Agent user, the size of the two input fields is inconsistent. Additionally, the placeholder text in the first input field is truncated due to insufficient space, making it unreadable. |  | Bug | Medium | Minor |  | - Both input fields should have the same size. - The placeholder text in the first input field should be fully visible without truncation. | https://drive.google.com/file/d/1J22i6kgSLFu-YcLexDskSMgwYKYtpIOY/view?usp=drive_link
8 | Payment | Input Field Size Mismatch and Placeholder Text Truncation | In the Payment module for the Customer user, the size of the two input fields is inconsistent. Additionally, the placeholder text in the first input field is truncated due to insufficient space, making it unreadable. |  | Bug | Medium | Minor |  | - Both input fields should have the same size. - The placeholder text in the first input field should be fully visible without truncation. | https://drive.google.com/file/d/1X4PUpC0jQPxS5PR42uI-UAKurY8K5Tht/view?usp=drive_link
9 | Send Money | Input Field Size Mismatch and Placeholder Text Truncation | In the Send Money module for the Customer user, the size of the two input fields is inconsistent. Additionally, the placeholder text in the first input field is truncated due to insufficient space, making it unreadable. |  | Bug | Medium | Minor |  | - Both input fields should have the same size. - The placeholder text in the first input field should be fully visible without truncation. | https://drive.google.com/file/d/1uyuns47-FH4O247E-3zFOUPy6SlF_EwF/view?usp=drive_link
10 | Statement | Export Button to Generate Statement Excel Sheet Not Working | The Export button in the Statement module is not functioning for the Customer user. When clicked, it fails to generate and download the Excel sheet. This issue affects the ability to export statements for analysis. |  | Bug | High | High |  | Clicking the Export button should generate and download the statement in Excel format. | https://drive.google.com/file/d/1ixkVW9KixlNbfkCG2YVIrLcrBkVMYoxb/view?usp=drive_link